## Slide 1: Satus of the projects for the improvment of the conditions for navigation in Romania 7th Workshop on the Follow-up of the Joint Statement on Guiding Principles on the Development of Inland Navigation and Environmental Protection in the Danube River Basin
Budapest, 15 – 16 September 2016

## Slide 2: Improvement of the conditions of navigation on the Danube on the sector: km 375 – km 175, Calarasi – Braila km 845.5 – Km 375, Romanian – Bulgarian common sector

## Slide 3: IMPROVEMENT OF THE NAVIGATION CONDITIONS ON THE DANUBE BETWEEN CĂLĂRAȘI AND BRĂILA, KM 375 –KM 175 The Contract for works was signed on April 2009 with the Consortium formed by INTERCONSTRUCT Ltd., CANAL SERVICE Ltd., SUPERQUATRO GRUP Ltd. and G&G Ltd. Contract Price: 38,671,752.12 Euro (85% CF and 15% state budget) Implementation period: August 2011 – December 2016 ENVIRONMENTAL MONITORING CONTRACT The contract was signed in March 2011 with the Consortium formed by INCDPM (Romania), SC AQUAPROIECT SA (Romania), VITUKI (Ungaria), BOKU (Austria) and DMG (România) Contract Price: 8,140,706 Euro (85%ERDF and 15 % state budget SOPT 2007 – 2013 and Large Infrastructure Operational Programe 2014 - 2020) Implementation period: April 2011- April 2017 FEASIBILITY STUDY FOR ALTERNATIVE SOLUTION ON BALA BRANCH The contract was signed in February 2015 with the Consortium EGIS EAU France, EGIS Romania, Compagnie Nationale du Rhone. Contract Price: 794,786.81 Euro Implementation period: February 2015 – December 2016

## Slide 4: 10 critical points identified 3 were considered first priority to be executed in phase I PC 01 –Bala Branch area and Caragheorghe sand –banks protection –guiding dyke –bottom sill –dredging PC 02 –Epuraşu Island Area –banks protection –submersible guiding dyke PC 10 –Caleia Branch (Ostrovul Lupu) –banks protection on the left bank of the Danube, on the right arm of the Caleia Branch and on the left side of the Caleia Branch –bottom sill –dredging

## Slide 5: Current situation: AFDJ has stopped the execution of the bottom sill at a 50% lower level formed only from the sand bags core of the originally designed bottom sill secured with a rock armour layer and is not a wall but is trapezoidal structure with very gentle slopes. The final level will be “0” m Black Sea Constanta. The works in Bala have been completed 100% and taken over in April 2016. 2 solutions are currently under 3D mathematical modelling process. the 3D modelling Report in 2 weeks. Description of solution 9 will be sent to the stakeholders and discussed during the meeting of the Working Group -Danube organised by the Ministry of European Funds on 20th September 2016.

## Slide 6: Transparency All the monitoring team reports, drafts and final versions are posted on the AFDJ website the http://www.afdj.ro/rmd_ro.html. Other relevant information on the INCDPM website www.incdpm.ro 6 workshops with Romanian authorities, European Commission, ICPDR, stakeholders June 2012 February 2013 July 2013 October 2013 May 2015 October 2015 After AFDJ will receive the 3D modelling Report, another workshop will be organised.

## Slide 7: Transparency Since the last workshop in October 2015, EGIS team created an online platform where the following items have been uploaded for your information : Alternative solutions report –draft – January 2016 Measurements data Consultant (EGIS – CNR) measurements data Measurements report BOKU Raw data DELTARES Raw data This platform is still functional and can be accessed through the following URL is : https://proeurope.egis.fr/water/ROU/BALA/C__Collaborative_Zone LOGIN : egis\c.cuc PASSWORD : Mpa62S7W On this folder, the various stakeholders will be able to download or upload content, or review and comment documents online. This folder has to be considered as a collaborative tool, that allows EGIS team to work more efficiently on the Bala branch project.

## Slide 8: FAST DANUBE - Technical Assistance for Revising and Complementing the Feasibility Study Regarding the Improvement of Navigation Conditions on the Romanian-Bulgarian Common Sector of the Danube and Complementary Studies Project period : November 2014 – Decembre 2018 Project budget: 5.252.000 euros (85% FC and 15% state budget, Connecting Europe Facility) During the tender procedure 8 offers were submitted and the evaluation process started on 17th March 2016. Estimated time for signing the contract: October 2016.

## Slide 9: Select the ‘critical’ river sections ; Undertake the necessary hydrological, hydrographical, topographical and sediments surveys; Prepare design alternatives (including dredging requirements) – fully considering as well the environmental protection objectives. Prepare the necessary mathematical models; Perform the Interdependency Test; Apply all new data and mathematical modelling results for proposing preliminary designs which use the proposed engineering solutions (dredging, groins, sills, chevrons etc.) and where possible non-structural measures Compare and rank the design alternatives in terms of their technical feasibility and effectiveness; Quantify the impact of the various designs on the Natura 2000 sites.

## Slide 10: Organisational structure INEA supports the EC in the management of CEF projects. The INEA Project Officer reports every decision from EC and monitors the project progress and approves all the reports delivered by the project consortium. Advisory Council (AC) consists of the Project Management Team (PMT) and non-project related stakeholders of the inland navigation sector in the Danube corridor. AC will meet twice per year during the project and will be chaired by the Project Manager. The Advisory Council will not make formal decisions on the project, but will collect and reflect inputs and trends relevant for the implementation of the project.

## Slide 11: Organisational structure Steering Committee (SC) takes the major management decisions. SC is made up of members of the Project Management Team (PMT) and representatives of key institutions playing a role in the implementations of Fast DANUBE project: Romanian Ministry of Transport, Bulgarian Ministry of Transport, Romanian Ministry of Environment, Water and Forest, Bulgarian Ministry of Environment and Waters, Harbour administrations from Romania (Romanian Danube River Port Administration), Republic of Bulgaria (Bulgarian Port Infrastructure), Romanian Ministry of European Funds.

## Slide 12: Organisational structure Stakeholer Forum – 5 meetings/project During the EIA procedure are foreseen ten session of public consultations and five Stakeholders FORUM. Public consultations will be conducted in accordance with Romanian and Bulgarian legislation as well as Convention on Environmental Impact Assessment in a Transboundary Context done at Espoo.

## Slide 13: Thematic Working Group for the implementation and monitoring of the projects related to the improvment of the navigation conditions on the Danube First meeting: 23.08.2016 Next meeting: 20.09.2016 Members: Ministry of European Funds Ministry of Transport Ministry of Environment, Waters and Forests National Agency for Environment Protection River Administration of the Lower Danube Navigable Canal Administration Romanian Shipowners and Port Operators Association Romanian Academy – Biologic Institute WWF – Danube – Carphatians Programme Romanian Trade and Industry Chamber Institute for Public Policies

## Slide 14: Thank you for your attention ! Ministry of Transport of Romania Naval Transport Directorate tel. 0040 21 319 62 03 fax 0040 750 032 441