## Slide 1: Rehabilitation and Development of the Navigation and Transport on the Sava River Waterway
7th Joint Statement Implementation Meeting,
Budapest, September 15-16, 2016

## Slide 2: Project Description-Measures
Identified need for improvements (Preliminary Design):
  Training works and dredging (19 locations)
  River bend improvements (20 locations)
  Bridges (3 locations)
  River Information Services
Estimated construction costs (rkm 0-rkm 594):
  Class IV: 80,7 mil. EUR
  Class Va: 86,4 mil. EUR

## Slide 3: Current Project Status-sector Brčko (rkm 234) – Sisak (rkm 594)
The preparation of the detailed design and all necessary documentation for the works was launched on May 16, 2013.
During the inception phase, based on the analysis of the existing documentation and the consultation with environmental stakeholders, the consultant proposed increasing the scope of work, as well as the extension of time for the completion of the Project.
Republic of Croatia agreed in principle with the need for further additional work and secured financing for it.
The Project is currently suspended due to the administrative reasons.

## Slide 4: Current Project Status-sector Brčko (234) – Belgrade (0)
Financing of the EIA Study, detailed design and demining of the BiH river bank was agreed with the EU and World Bank (IPA BiH).
On May 8, 2014, the EU and World Bank cancelled the agreement for financing of the development of the EIA Study, detailed design and demining for the Sava Waterway Project due to internal administrative problems in BiH.
BiH and Serbia are considering the possibilities for financing of the continuation of the Project on this sector.

## Slide 5: The interim measures
The most critical sector: Novi Grad rkm 320 – rkm 329.

## Slide 6: Water level 2013 for the sector Novi Grad

## Slide 8: The interim measures
The border sector Croatia-B&H, coordination trough Sava Commission
Aim is 280 days with 2,3 m depth per year; no stoppage of navigation at any time due to the dimensions of the fairway
Project Committee established by SC Decisions 7/11 and 11/12 will be activated also for the implementation of this measures
In line with the Luxembourg Declarations and Master Plan
Implementation of the conclusions from The Ministerial meeting of Sava Countries on regional cooperation in the field of waters held on July 6, 2015

## Slide 9: Final remarks
Rehabilitation of the mentioned most critical sector will not be sign to drop of the project for the rehabilitation of the entire waterway of the Sava River, whose implementation only guarantees the possibility of a permanent increase in traffic on the waterway and the full utilization of economic potentials in areas along the Sava River
The rehabilitation of the navigation and transport on the whole Sava River Waterway remains one of the priorities for the Sava Commission Member States.

## Slide 10: More information
www.savacommission.org

## Slide 11
Thank you for your attention!!!
Željko Milković